## Product Backlog
INFT 3000 Capstone Project - eShopper Application
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint | Complete
interface for client (CI) |  | yes | high |  | 8 | 1 | 8
interface for vendor (VI) |  | yes | high |  | 8 | 1 | 8
store selector in CI
test-ERD for vendor inventory |  | yes | medium |  | 5 | 1 | 5
login for each interface
test-database for items
CRUD for clients in VI
store selector in CI
item menus in CI
grocery sorter for VI
list of orders in VI
documentation |  | yes | low |  | 3 | 1 | 3
manager permissions
dept manager permissions
regular permissions
set up version control |  | yes | medium |  | 5 | 1 | 5
erd for users |  | yes | medium |  | 5 | 1 | 5
[5 empty] | 34 |  | 34

## Sprint 1 Backlog
INFT 3000 Capstone Project - eShopper Application
Sprint 1
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1/2 | Day 3/4 | Day 5/6 | Day 7/8 | Day 9/10 | Sprint Review
documentation | 3 | Sean | in progress | 4 | 3 | 2 | 2 | 2 | 2 | 2
interface for client (CI) | 8 | Jordan | in progress | 8 | 6 | 5 | 4 | 4 | 4 | 4
interface for vendor (VI) | 8 | Trent | in progress | 8 | 6 | 6 | 5 | 5 | 5 | 5
ERD for users | 5 | Trent | complete | 5 | 4 | 1 | 1 | 1 | 1 | 1
test-ERD for vendor inventory | 5 | Andrew/Sean | in progress | 5 | 5 | 5 | 4 | 4 | 4 | 4
set up version control |  | Andrew | complete | 1 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 31 | 24 | 19 | 16 | 16 | 16 | 16

## Sprint 2 Backlog
INFT 3000 Capstone Project - eShopper Application
Sprint 2
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 3 Backlog
INFT 3000 Capstone Project - eShopper Application
Sprint 3
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 4 Backlog
INFT 3000 Capstone Project - eShopper Application
Sprint 4
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Citations
Citations: